## Project Plan
Project Plan - Planned
Project Name: | Entertainment Event Application
Project Lead: | Nicholas Packham*
Project Plan Author: |  | Nicholas Packham
Planned Start Date: |  | 2023-02-06
Planned Finish Date: |  | 2023-03-31
*Project Leader not offically confirmed
|  |  | February |  |  |  |  | March
|  |  | Meeting | Meeting | Meeting | Meeting | Meeting | Meeting | Meeting | Meeting | Meeting
Generic Tasks |  |  | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27
Weekly meeting agenda | bar: 2023-02-06 to 2023-03-27
Document meeting notes |  |  | AM | HM | NP | AM | HM | NP | AM | HM | NP
Update Trello board |  |  | HM | HM | HM | ALL | ALL | ALL | ALL | ALL | ALL
Upload NEW doucments to GitHub |  |  |  | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL
|  |  | February |  |  |  |  | March
|  |  | Meeting | Meeting | Meeting | Interim Report | Meeting | Meeting | Meeting | Meeting | Meeting | Final Report
Specific Tasks |  |  | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-24 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-03-31
Project decisions |  |  | 2023-02-06: ALL
Project plan | bar: 2023-02-06 to 2023-02-13
Create GitHub repo | bar: 2023-02-06 to 2023-02-13
Create Trello board | bar: 2023-02-06 to 2023-02-13
Research project |  |  | 2023-02-06: ALL; 2023-02-13: ALL
Produce a basic case study on the chosen project |  |  | 2023-02-06: ALL; 2023-02-13: ALL
Basic design draft of chosen 'event' for application |  |  | 2023-02-13: ALL; 2023-02-20: ALL
Basic explanation of the logic used for chosen 'event' |  |  | 2023-02-13: ALL; 2023-02-20: ALL
Interim Project Report |  |  | 2023-02-20: ALL; 2023-02-24: ALL
Design chosen 'event' for application within Figma |  |  | 2023-02-27: ALL; 2023-03-06: ALL
Assign each team member 'common' application screens to design. E.G. screens like 'Dashboard', 'Help page', etc. |  |  | 2023-02-27: ALL; 2023-03-06: ALL
Feedback to be provided for Figma designs |  |  | 2023-03-06: ALL
Update Figma designs as per feedback |  |  | 2023-03-06: ALL; 2023-03-13: ALL
Combine all designs together in Figma and create a single prototype for the final report (presentation) |  |  | 2023-03-06: ALL; 2023-03-13: ALL
Final Project Report |  |  | 2023-03-13: ALL; 2023-03-20: ALL; 2023-03-27: ALL; 2023-03-31: ALL